## Sheet1
Estimated total probable cost for budgeting - Schematic design phase
AV Adult Ed Building | Quantity | Unit | Cost / Unit | Total | Notes
Phase 1 Sitework
Site demo | 46110 | sf | 6 | 276660 | Demo fencing, trees, paving, etc.
Site grading | 46110 | sf | 3.22 | 148474.2
4" Concrete walkways | 10335 | sf | 38 | 392730 | Concrete around the building
Landscaping | 6450 | sf | 12 | 77400 | City of Palmdale will require a minimum of 10% of lot area to be landscaped
AC Paving | 15433 | sf | 35 | 540155 | Paving east side between building and southern parking
Site utilities | 1 | ls | 230000 | 230000 | Covers sewer, water, gas, electrical - dependant on existing site utilities (does not include service upgrades, and utility offsite connection fees if required)
Phase 1 Sitework sub-total |  |  |  | 1665419.2
Phase 2 Site
Site demo | 21518 | sf | 6 | 129108
Site grading | 21518 | sf | 3.22 | 69287.96
AC Paving | 15433 | sf | 35 | 540155
Phase 2 Sitework sub-total |  |  |  | 738550.96
Phase 1 Building Shell
Pre-engineered Metal Building (14,000SF) | 1 | ls | 642922.93 | 642922.93 | CBC Quote Dated 09.27.2024
Building erection | 14000 | sf | 60 | 840000 | Estimate based on CWA per local erector
Concrete Foundations | 14000 | sf | 60 | 840000
Mezzanine | 1100 | sf | 60 | 66000
Building Shell sub-total |  |  |  | 2388922.93
Tenant Improvements
Phase 1 Interior Build Out | 7550 | sf | 200 | 1510000 | Lounge, Offices, Restrooms, Custodial, Storag, Woodshop, Metal Shop, Corridors
Phase 2 Interior Build Out | 6450 | sf | 200 | 1290000 | Dental, Arts, VR Classrooms
Building Tenant Improvement sub-total |  |  |  | 2800000
Phase 1 Sub-total |  |  |  | 5564342.13
Phase 2 Sub-total |  |  |  | 2028550.96
Phase 1 Costs
Hard Cost Total |  |  |  | 5564342.13
Soft Project Costs (20%) |  |  |  | 1112868.426 | Project reports, City Fees, Permits, AE Fees, Inspections
Hard & Soft Costs Subtotal |  |  |  | 6677210.556
Overall Contingency (10%) |  |  |  | 667721.0556 | 10% contingency at this stage of the project is standard
Phase 1 Estimated Project Cost |  |  |  | 7344931.6116
Phase 2 Costs
Hard Cost Total |  |  |  | 2028550.96
Soft Project Costs (10%) |  |  |  | 101427.548 | City Fees, Permits, AE Fees, Inspections
Hard & Soft Costs Subtotal |  |  |  | 2129978.508
Overall Contingency (10%) |  |  |  | 212997.8508 | 10% contingency at this stage of the project is standard
Phase 2 Estimated Project Cost |  |  |  | 2342976.3588
Total Estimate Project Cost |  |  |  | 9687907.9704