Pacific Grove Adult Education (PGAE) 2024-2025 Carryover Expenditure Plan:

Carry Over Funding to be Allocated: $636,857

| One Time Cost Projects: |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Item: | Budgeted Cost | YTD Cost: | Budget Category | Progress | Details of Project: | Est Completion Date |
| Portable needed to expand CTE program | 110,000 | 28,800 + 25,625 encumbered | 6000 | In progress | In planning phase (costs this year include land survey and architect schematic and quotes) | This phase should be completed by June 2025 |
| Computer Lab upgrade | 8,000 | 8,000 | 5000 | Complete | Updated instructional technology and equipment | July 2024 |
| IPP Hospitality Pathway equipment | 26,000 |  | 6000 | In progress | Schematics, permits, quotes and purchasing in progress for coffee cart and cafe kitchen | June 2025 |
| Parent Education/Engagement training contract | 14,100 | 14,100 | 5000 | Complete | PGAE and Monterey Adult School PGAE in collaboration with MAS to provide Parent Education Classes for Student Success, covered this expenditure | May 2025 |
| Parent Education/Engagement curriculum | 17,265 | 17,300 | 5000 | Complete | PGAE and Monterey Adult School PGAE in collaboration with MAS to provide Parent Education Classes for Student Success, covered this expenditure | May 2025 |
| Parent Education/Engagement supplies | 2,000 | 500 | 4000 | In progress | Materials and supplies needed for parent trainings at PGAE | May 2025 |
| Professional Development | 43,000 | 10,483 | 5000 | In progress | CAEP Summit, CATESOL, CalPro, TESOL, ACSA, CCAE, CASAS, Family Leadership, CPR/First Aid, Van Driver Training | June 2025 |
| MPAEC Needs Assessment | 11,250 | 11,250 | 5000 | In progress | Pedroso Consulting contract (¼) for needs assessment to inform consortium 3-year plan | April 2025 |
| Entravision advertising campaign | 13,350 | 5,350 | 5000 | In progress | Portion of summer/fall 2024 campaign ($5,350) and new 2025 Entravision contract (⅓ = $8K) (one phase of campaign in March-April, second phase in July-Sept) for regional MPAEC advertising in English and Spanish via TV, radio, and digital advertising | September 2025 |
| N&R Publications marketing campaign | 26,000 |  | 5000 | In progress | N&R Publications contract for articles and digital and print publications to highlight PGAE programs and student success stories |  |
| Personnel and/or Ongoing Expenditures |  |  |  |  |  |  |
| Parent Education/Engagement instructors | 25,139 | 3,361 | 1000-3000 | In Progress | Instruction for parent train-the-trainer classes at PGAE |  |
| Salary/Benefit increases in 24/25 school year | 340,753 |  | 1000-3000 | In Progress | Difference between .88% CAEP COLA and PGUSD COLA (4.87%) -- total was $483,971, using carryover to cover part |  |
| Estimated Totals: | 636,857 |  |  |  |  |  |

One time costs/projects: $270,965

Personnel ongoing: $365,892 (includes a large portion of 24-25 sal/ben increases; hopefully we’ll have a bigger COLA in 25-26 (projected 2.43% based on CAEP preliminary budget))  To help cover the cost of this increase in expenditures.

*PGAE total budget expenditures are at 58% spent YTD on track to expend 100% at the end of Q4.  Technically, we have spent down all 23/24 carryover according to our FIFO report in NOVA.